## Sheet1
Team Meetings |  |  |  | Members attending
|  |  |  | name | name | name | Notes and actions
Meeting Number | Date | Start time | End time | Kyle | Mariano | Krystal
1 | 2024-04-03 | 2:00 | 3:00 | x | x | x | Created a GitHub repository to share our code together. Initial talks about how we were gonna combine the work amongst ourselves.
2 | 2024-04-10 | 1:50 | 2:30 | x | x |  | Made progress: Mariano to start on extension, Texted Krystal to help make sure code works together(Got No Response), Kyle helping create Gui interface
3 | 2024-04-19 | 3:00 | 4:00 | x | x |  | Met outside of class time to check in and make sure our code was working when put together. Talked about starting presentation. Krystal still no response
4 | 2024-04-21 | 12:30 | 1:30 | x | x |  | Krystal texted on Saturday saying she dropped the class a bit back but she didn’t inform us until today. Mariano and Kyle scramble to get finishing pieces.